## Slide 1
Thomas G. Gardner CAPSTONE Program Manager Advanced Space, LLC
Delivering Innovation to Orbit™
The Cislunar Autonomous Positioning System Technology Operations and Navigation Experiment (CAPSTONE): A Summary of a Highly Successful Mission Currently Operating in the Cislunar Environment

## Slide 2: CAPSTONE Mission Summary
What is CAPSTONE?
A 12U CubeSat that will serve as the first spacecraft to enter into the Near Rectilinear Halo Orbit (NRHO) destined for Gateway, the Moon- orbiting outpost that is part of NASA’s Artemis program.
CAPSTONE is the first CubeSat to fly in cislunar space.
Successfully launched on June 28th @ 5:55AM EDT aboard a 3-stage Rocket Lab Electron rocket from Mahia, NZ.
~4 months in deep space to arrive at its target insertion into the NRHO via a low-energy, deep space transfer using a hydrazine propulsion system.
Insertion into the NRHO occurred on November 13, 2022
Scheduled to orbit this area around the Moon for up to 18 months to understand the characteristics of the orbit and perform technology demonstrations.
Helping reduce risk for future spacecraft by validating innovative navigation technologies and verifying the dynamics of the NRHO.
2

## Slide 3: CAPSTONE Mission Objectives
Validate and demonstrate NRHO/three-body Earth-Moon operations.
Objective 1 is focused on mitigating technical uncertainties associated with operating in the uniquely beneficial and challenging orbital regime defined as Near Rectilinear Halo Orbits. This objective will include demonstrating navigation capabilities and validating station keeping simulations. Complete
Inform future lunar exploration requirements and operations such as for the Artemis Lunar Gateway.
Objective 2 is focused on building experience operating in complex lunar orbital regimes to inform future lunar exploration requirements and operations, including human exploration flights with lower risk thresholds and higher certainty of success requirements. This will include the establishment of commercially available capacity to support NASA, commercial, and international lunar missions in the future. On track
Demonstrate and accelerate the infusion of the Cislunar Autonomous Positioning System (CAPS).
Objective 3 is focused on demonstrating core technical components of the Cislunar Autonomous Positioning System (CAPS) in an orbital demonstration. This objective will include collaboration with the operations team at NASA Goddard Space Flight Center to demonstrate inter-spacecraft ranging between the CAPSTONE spacecraft and the Lunar Reconnaissance Orbiter in operation at the Moon. In addition to demonstrating key inter-spacecraft tracking, CAPSTONE will also enhance the technology readiness level of the CAPS software. On track
Notes: EOT: 3:00
TGO: 12:00
Narrate each objective
1) emphasis on operations and nav uniqueness
2) supporting the operations and support requirements for NRHO ops
3) CAPS - ranging enables autonomous navigation thus reducing earth based systems support

## Slide 4: CAPSTONE Mission Timeline Months from Launch
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
L + 4 |  |  |  | L + 5-10 months: Conduct primary demonstration operations for 6 months NRHO operations and flight dynamics assessment CAPSTONE to LRO cross-link experiment One-way ranging with the CSAC |  |  |  |  |  |  | L + 10-22 months: |  |  |  |  |  |  |  |  |  |  |  | Possible follow-on Ops with other NASA or commercial assets End of mission (EOM) - Spacecraft disposal |  | 
months: Launch to LEO Orbit |  |  |  |  |  |  |  |  |  |  | Conduct technology enhancement operations for 12 months Perform additional NRHO operations and |  |  |  |  |  |  |  |  |  |  |  |  |  | 
raising BLT & insertion |  |  |  |  |  |  |  |  |  |  | autonomous system evaluation Continued CAPSTONE to LRO and 1-way ranging experiments |  |  |  |  |  |  |  |  |  |  |  |  |  | 
into |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NRHO by |  |  |  |  |  |  |  |  |  |  | Increase fidelity of CAPS system demonstration |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CAPS- TONE S/C |  |  |  |  |  |  |  |  |  |  | Detailed demonstration of a one-way ranging experiment with the Chip Scale Atomic Clock (CSAC) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4
Today: 5/1/23

## Slide 5: CAPSTONE Spacecraft
Fully Assembled Spacecraft/Dispenser
5
Subsystem | Value
Battery Modules | QTY 3x, 182 W-hr storage
Solar Panels | Deployable Fixed Angle Arrays, Peak Power 114W (BOL), 120 XTJ Prime cells
Space / Ground Radio | Iris Radio, 3.8W, operating at 8.45 GHZ downlink, 7.19 GHz receive
Space / Ground Antennas | X-band high gain & low gain patch antennas, on spacecraft Y- and Y+ faces
LRO Crosslink Radio | TUI SLX, 2W, operating at 2.091 GHz transmit, 2.271 GHz receive
LRO Crosslink Antenna | S-band patch antenna on Z+ face
ADCS Control | Coarse sensor module, redundant star trackers, redundant IMUs with STIM 320 10g, four pyramidal reaction wheels
Thermal Control | Active battery heaters, 16 thermistor channels, 8 independent heaters, passive coatings and MLI
Propulsion | 8x 0.25N thrusters, 3.25 kg fuel, >200 m/s ΔV

## Slide 6
CAPSTONE Spacecraft in Flight Configuration
6

## Slide 7: Rocket Lab Launch Support Launch from LC-1, Mahia NZ
Pad
Lunar Photon
Fueling Facility
CAPSTONE Integrated Stack
7

## Slide 8: CAPSTONE Launch – Mahia, NZ June 28, 2022, 2:55 AM PDT
8

## Slide 10: Initial Acquisition and LOS Anomaly
Confirmation of downlink signal ~40 min after deployment on DSN Madrid
Spacecraft detumbled and commissioned successfully
Hand-off to Goldstone was successful
Minutes later lost signal on 04 July 2022 19:55 UTC
MOC continuously sent commands in the hope that something would get through
DSN executed search pattern
OD team processed navigation data to determine best DSN antenna pointing
06 July 2022 13:24 UTC – 2 days after LOS spacecraft performed an autonomous desaturation maneuver
Change in state machine allowed radio to reset and carrier lock re-achieved
Telemetry showed healthy spacecraft – nominal operations resumed
Root Cause of Anomaly
  Mis-formatted “peek” command sent to spacecraft during attempt to confirm status of PN regenerative ranging
  Vulnerability in IRIS radio software led radio to lock-up and become unresponsive due to this command (has since been fixed)
  Fault Detection, Isolation and Recovery (FDIR) was in place to detect and resolve the issue seen on the IRIS but a FSW issue in the FDIR prevented autonomous recovery

## Slide 11: Low Energy, Ballistic Lunar Transfer (BLT)
Earth-centered
Inertial Frame
TCM- 1
TCM-5
TCM-6
NIM
TCM- 2
TCM-3
(Anomaly)
Moon’s Orbit
Earth
TCM-4
Apogee
1.437 M km from Earth
11
Maneuver | Designed DV (m/s) | Estimated DV (m/s) | Estimated Error
TCM-1a | 20.002 | 19.81 | <1%
TCM-1c | 1.631 | 1.618 | <1%
TCM-2a/b | 40.116 | 39.97 | <1%
TCM-3* | 2.271 | 2.417 | ~6.4%
TCM-4 | 4.190 | 4.372 | ~4.3%
TCM-5/6 | 1.284/1.852 | N/A | N/A
NIM | 17.944 | 18.07 | <1%
ICM-1 | 4.268 | 4.222 | 1.15%
ICM-2 | 3.843 | 3.838 | <1%
*Post-maneuver anomaly

## Slide 12: Stuck “Open” Thruster Anomaly – 9/8/23
TCM-3 executed nominally
During “braking” phase spacecraft spun up due to stuck “open” thruster
Burn abort tripped due to excessive rates
Spacecraft goes into safe mode
Vehicle settled at rotation of ~70°/sec, pointing ~77° from the Sun
Repeating ~5 min lock, ~50 min loss cycle as spacecraft charged enough to power on radio then lost power
Propellant freezes (tank temp at -7C)
Spacecraft team load sheds – able to run heaters enough to unfreeze the propellant after several weeks

## Slide 13: Recovery – 10/12/23
With propellant unfrozen, the prop system was tested
Spin rate increased to 105 deg/sec
Narrow down stuck thruster to #3 (axial) or #5 (rotational)
Terran Orbital GNC team builds detumble controller that is robust to stuck open thruster
Oct-7 – Detumble maneuver completed successfully, regain constant communication with ground
Oct-11 – Pressurization test executed to conclusively determine thruster #3 was stuck
CAPSTONE completed >500k rotations during the anomaly!
#5
#3

## Slide 14: Near Rectilinear Halo Orbit (NRHO)
The NRHO is the baselined plan for NASA’s Gateway.
This quasi-stable orbit minimizes the propellant required for orbit maintenance.
Offers a continuous view of Earth
Avoids and/or minimizes eclipses
Provides coverage of both the lunar North and South Poles
Orbital period ~6.5 days
Perilune ~3,500 km
Apolune ~71,000 km
9:2 Moon-Sun resonant orbit
Earth
Moon’s orbit
Inertial frame
Earth-Moon pulsating, rotating frame
14

## Slide 15: Operations Status – 5/1/23
Currently in NRHO
  Due to minimum maneuver magnitude threshold, only needed to execute OMMs 5, 10, 13, 18, 20, 21
  No issues through eclipses (6 thus far): ~60-75 min each.
  Executed 3 CAPS attempts
  Have reduced DSN passes – needed fewer than one a day
Milestones:
  Executed 6 OMMs to maintain NRHO
  Performed 3 CAPS Crosslink attempts with LRO
Upcoming events
  Next CAPS Crosslink attempts planned May 9
  CSAC one-way ranging navigation demonstration May 15

## Slide 16: OMM Design Performance
OMM | Design (m/s) | Reconstruction (m/s)
1-4 | 0.0503 | Skipped
5 | 0.6192 | 0.6337 +/- 3.439e-3
6-9 | 0.2492 | Skipped
10 | 0.3143 | 0.3203 +/- 1.242e-6
11-12 | 0.2062 | Skipped
13 | 0.1868 | 0.1852 +/- 3.734e-6
14-17 | 0.3224 | Skipped
18 | 0.4499 | 0.4273 +/- 0.01493
20 | 0.1553 | 0.1654 +/- 2.218e-3
OMM Design Process:
Does the OMM, as designed, achieve the targets?
Does the performing the OMM keep CAPSTONE in the NRHO longer than if skipped?
When including navigation uncertainty and maneuver execution errors, does the OMM still effectively move the downstream state towards the target (or is the effect lost in the uncertainty)
Despite skipping many OMMs, the stationkeeping strategy keeps the spacecraft near the design reference

## Slide 17: CAPSTONE CAPS Demonstration Autonomous Absolute Navigation Experiment
S-Band Crosslink with LRO:
CAPSTONE Tx/Rx: 2091/2271.2 MHz
LRO
CAPSTONE
Crosslink Radio: Swift SLX
The cross-link experiment between CAPSTONE and the LRO spacecraft will evaluate ranging capability.
The Cis-Lunar Autonomous Positioning System (CAPS) will be demonstrated for lunar missions to utilize automated navigation solutions to reduce ground segment burden and enhance future mission operations.
To date , CAPSTONE has performed 3 ranging passes with the LRO spacecraft in order to generate absolute estimates of spacecraft position and velocity.
Results thus far have been uneven but promising. Working to adjust the CAPSTONE S-Band radio modulation and the ranging signal to get better measurements.
17

## Slide 18: CSAC 1-Way Ranging Experiment
A Chip Scale Atomic Clock (CSAC) has been added to Iris X-Band radio in order to support a 1-Way ranging experiment during the CAPSTONE mission.
Collaboration with JPL to develop the Iris interface to the CSAC
JPL has tested the ranging function and the firmware interface in their Iris testbed.
Tyvak completed the integration of the CSAC board package, the Iris transponder and the spacecraft SW interface in July 2021.
Advanced Space developed the 1-way ranging (uplink) navigation measurement processing software and delivered the flight SW for test in October 2021
Goal/plan is to test the 1-way ranging with the CSAC/Iris (DSN to spacecraft) during the enhanced mission phase as soon as mid-May, 2023
CSAC Board Package
18

## Slide 19: CAPSTONE Development Timeline
6/28/22
Project
KO
9/18/19
SRR/
MCR
10/16/19
PDR
12/4/19
CDR
2/28/20
SIR
7/30/20
ISR
DCDR
5/7/20
11/13/20
TRR
2/5/21
DTRR-1
STPR
S/C Ship Readiness
8/13/21
4/19/21
ATP
8/30/19
DTRR-2
LDR
2020
2021
2022
48
97
526
442
813
716
11/19/21
183
252
336
964
1036
Baseline schedule at ATP: 548 days (18 months)
Re-baseline 1 : 655 days (22 months) - Launch Vehicle Readiness, Spacecraft HW Development Issues
Re-baseline 2 : 782 days (26 months) - Launch Vehicle Readiness, Spacecraft HW Development Issues
Re-baseline 3 : 933 days (30 months) - Launch Vehicle Readiness, Spacecraft Testing
Re-baseline 4 : 974 days (32 months) - Launch Vehicle Readiness, Spacecraft Testing
Re-baseline 5: 1036 days (34 months) - Launch Vehicle Readiness, Spacecraft Testing Close-out
Fully 8 months of the ~16-month launch delay were due to complications due to COVID: Supply chain, personnel, launch vehicle upper stage testing and development. The remaining 8 months are due to risk realizations for the spacecraft and launch vehicle HW development and implementation.
MORR
5/19/22
Launch
19

## Slide 20: CAPSTONE: Key Lessons Learned - 1 of 2
For a CubeSat/Small Sat based mission with a clear set of mission goals, a better understanding of the overall system requirements is needed well before the PDR and certainly as part of the spacecraft acquisition process (i.e., RFP, contract requirements, deliverables, etc.)
  Low-cost, CubeSat missions often rely on COTS components and alleged “plug and play” designs that are often not as developed as advertised.
  A clear understanding of the unique requirements vs. capabilities for a unique mission needs to be better defined and detailed out BEFORE schedules and budgets are estimated and agreed to.
  Ground system requirements and operations are often not well understood until well after ATP and the complications related to those can drive schedule and costs that were not well considered. Plugging into existing ground architectures is not as simple as it is often advertised and the complexities of interface testing with those system is often underestimated.
Having a better understanding of vendor capabilities, heritage and past performance is important to understand prior to contract award and execution. Smaller, lower cost vendors often underestimate or underbid the costs and scope of the required work, and this leads to headaches and delays when inevitable problem arise.
20

## Slide 21: CAPSTONE: Key Lessons Learned - 2 of 2
Regulatory approvals often require far more time and resources that expected
  Frequency approval for cislunar or deep space missions is often a labyrinth of requirements and approvals that require extensive attention to the detailed requirements and the time it takes to receive full approval.
  Multiple government agencies, who often don’t communicate with each other, are involved in getting final launch approval, i.e., New Zealand Space Agency (NZSA)
  Items like Planetary Protection, Orbital Debris, Range Safety requirements for launch, and transport requirements for an overseas launch (aka Rocket Lab in NZ) are not well understood by most space systems development teams and require significant oversight by project management.
Selling the project is great. Implementing and executing the project is ALWAYS harder, takes longer and costs more that most everyone thinks.
  CAPSTONE was sold as a low cost, fast paced cislunar mission to deliver data and results to NASA in
~20-24 months. The reserves were considered adequate and that is often underestimated as well.
  COVID aside, several key challenges were not well understood by the team until well into the project and costly adjustments had to be made to mitigate these issues.
  Between the launch vehicle upper stage issues and the the unique spacecraft requirements impact on a COTS design, the mission launched ~16 months after it was initially planned.
21

## Slide 22: CAPSTONE Mission Status – 5/1/23
CAPSTONE has successfully operated in the NRHO since 11/13/22 (167 days)
All six(6) Orbital Maintenance Maneuvers (OMM’s) have successfully executed as planned. Multiple planned OMM’s have been cancelled cancelled due to process of stepping down DV to find a lower bound threshold.
OMM cadence reduced due to minimum OMM DV based on the updated Terran controller implemented for the post-TCM-3 valve anomaly.
Due to updated maneuver performance, further threshold reductions are expected to reduce the minimum OMM < 5 cm/sec.
Two anomalies has occurred since NRHO insertion: Loss of commanding on uplink occurred on Jan. 26th and Feb 17. Suspect SEU on the Iris firmware as the root cause. Commanding restored on Feb 6th and Mar 1st when Command Loss Timer reset the spacecraft.
First CAPS pass attempt occurred on 18 Jan. LRO received a signal, but no ranging data was observed. Two additional passes have been successfully executed with data collected but the ranging data was now well characterized.
Next CAPS pass attempt (lower range to LRO) is planned for 5/9/23. Working the TUI on adjustments to the ranging modulation to improve the measurement quality.
CAPS SW Version 0.5 continues development and will be part of potential in flight SW updates to improve the accuracy of the navigation estimate and correct issues observed in the initial experiment’s results.

## Slide 23: AIAA 2022 SmallSat “Mission of the Year” Awarded at 2022 SmallSat Conference – 8/10/22
23
Award Cube!

## Slide 24: Questions and Additional Information?
Email: gardner@advancedspace.com
Thank-you!
AdvancedSpace.com/missions/capstone
NASA.gov/directorates/spacetech/small_spacecraft/capstone
24

## Slide 25
(CAPSTONE)
Cislunar Autonomous Positioning System Technology, Operations, and Navigation Experiment
Demonstrating an innovative spacecraft-to-spacecraft navigation solution at the Moon from a near rectilinear halo orbit slated for Artemis' Gateway.
The CAPSTONE mission is managed by NASA's Small Spacecraft Technology Program. NASA's Advanced Exploration Systems funds the launch and supports mission operations. The mission is developed and operated by Advanced Space, LLC.
Delivering Innovation to Orbit™

## Slide 26: Artemis Project Relationship to CAPSTONE
Advanced Space is currently (independent of CAPSTONE) supporting the Artemis program at NASA JSC with orbit design and navigation trades studies and analysis related to the overall mission design and operation planning for the Gateway Program.
This effort began ~3 years ago to support analysis and understanding of orbit transfers, orbit operations, navigation and OMM (Orbit Maintenance Maneuver) planning in the Near Rectilinear Halo Orbit (NRHO).
This existing work, and these existing relationships provide an expedited transition of lessons learned and knowledge between programs/activities.
A major objective of CAPSTONE is the validation of those analysis efforts in support of development and planning for the Gateway Program.
“The purpose of flight research is to separate the real from the imagined problems and to make known the overlooked and the unexpected.” - Hugh L. Dryden
26

## Slide 27: CAPSTONE Quantifiable Objectives
Demonstrate a rapid and affordable lunar mission by reaching initial launch readiness no later than 18 months from authority to proceed (contract award: 8/30/19, COVID delays not withstanding). 33 months.
The CAPSTONE mission shall demonstrate a low-energy transfer to cis-lunar space requiring no more than 120 m/s DV when provided a -0.6 km2/sec2 C3 that can be achieved by a commercial small launch vehicle. Fully executed successfully – 94.21 m/sec (actual through ICM-2).
For comparison to the predicted value, measure the DV to within +/- 3 m/s for insertion into a 9:2 synodic resonant lunar NRHO. Fully executed successfully on 11/19/22 (< 1% error).
For comparison to predicted values, collect spacecraft position data to within +/- 10 km, collect spacecraft velocity data to within +/- 10 cm/s, and measure the required station keeping budget to within +/- 1 m/s DV over a minimum of 6 orbits a 9:2 synodic resonant lunar NRHO. Ongoing. Thus far: 7.5 cm/sec per rev of the 24 NRHO orbits.
The CAPSTONE mission shall test the CAPS system’s ability to generate a navigation solution to within 10 km in position and 10 cm/s in velocity without Earth-based tracking data by comparing the onboard flight software solution with ground-based results for at least 5 tracking passes with the measured signal noise on the LRO crosslink factored in. Ongoing. 3 attempts thus far. Partially successful. Next CAPS pass attempt on 5/9/23.
Document operational experience and lessons learned for insertion into and operation in a lunar NRHO and directly transfer that experience and lessons to the NASA Gateway team. Reviewed with multiple JSC Gateway team(s) in April 2023.

## Slide 28: Navigation Highlights Separation through NRHO Operations
Met all navigation requirements at the time of maneuver designs
  TCM-1a, TCM-1c, TCM-2, TCM-3, TCM-4, NIM, ICM-1, ICM-2, OMM-5, OMM-10, OMM-13)
Navigation through propellent “bake-off” for the entire mission and full line-leaks after the thruster valve anomaly
  Consistently estimating perturbations after each thruster event
Navigation during anomalous spin-stabilized period
  Calibrated out transmit frequency bias due to spin – two separate biases as a function of which antenna was being utilized
Navigation Post-ICM-2 in the NRHO has been nominal and well within the expected predicted NRHO performance.

## Slide 29: CAPSTONE Orbit Determination Performance Position, Velocity
Deployment to TCM-2 (Doppler only)
  ~10 km, ~1 cm/s 3-sigma
TCM-2 to TCM-3
  ~10 km, ~1-5 cm/s 3-sigma
TCM-3 to Anomaly Recovery (Spin-stabilized, Doppler only)
  ~5-20 km, ~0.8-2 cm/s 3-sigma
Anomaly Recovery to NIM
  ~1-3 km, ~0.5-1 cm/s 3-sigma
Post-NIM (Leadup to ICM-1, high tracking cadence)
  ~0.2-1 km, ~0.3-0.5 cm/s 3-sigma
Post-ICM 1, 2
  ~1 km, 5 cm/s 3-sigma
Post-OMM 10
  ~0.8 km, ~1 cm/s 3-sigma
Post-OMM 13
  ~1.207 km, ~1.43 cm/s 3-sigma

## Slide 30: CAPSTONE Propulsion System
CAPSTONE Propulsion Flight Unit
CAPSTONE ETU System Testing
30
Subsystem/Spec | Value
Dimensions | 2U X 2U footprint for 12U spacecraft
Fuel Capacity | Variable height for fuel load ~3-6kg
ΔV | ~220 meters/sec
Thrusters | 8 thrusters with 0.25 N thrust (200 sec Isp)
Attitude Control | Translational & 3-DOF rotational capability
Propellant | Hydrazine with catalyst decomposition
Pressurization | Electric gear pump
Launch Safety | 91-710 compliant, propellant tank not pressurized at launch, fully welded and sealed

## Slide 31: Mission Operations Architecture
Tyvak Mission Operations Center (MOC): spacecraft operation, monitoring, commanding
Advanced Space Operations Center (ASOC): orbit determination, maneuver planning, payload activity planning