## Slide 1
Lessons Learned Developing Lunar Flashlight Flight Software using the F Prime Product Line
Aadil Rizvi, FSW Engineer, NASA/JPL
Kevin F. Ortega, FSW Engineer, NASA/JPL
© 2023 California Institute of Technology. Government sponsorship acknowledged.

## Slide 2: Introduction
Lunar Flashlight (LF) CubeSat
Illuminate permanently shadowed regions and detect water ice absorption bands in the near-infrared.
6U CubeSat
First mission to use laser reflectometer to look for water ice
Launch date: Dec. 2022

## Slide 3: Lunar Flashlight Flight Software (FSW) Overview
Executes on C&DH platform (Sphinx)
Uses the open-source F Prime Product Line (https://github.com/nasa/fprime)
Leverages a common shared multi-mission software deployment developed for the Sphinx avionics platform using F Prime
  Developed concurrently with NEA Scout FSW

## Slide 4: F Prime Product Line
https://github.com/nasa/fprime
Open-source software framework for the rapid development and deployment of embedded systems and spaceflight applications

## Slide 5: Lunar Flashlight Hardware
Multi-mission Hardware
LF Specific Hardware

## Slide 6: Lunar Flashlight Flight Software
Chart: 
| F Prime, Sphinx Common and Auto-coded Software | LF Specific Hand Coded Software
Lunar Flashlight FSW SLOC Metrics | 94 | 6
Total SLOC = 320,985
94%
6%

## Slide 7: Lunar Flashlight Lessons Learned
Developing a baseline software deployment for common avionics hardware shared between LF and NEA Scout was invaluable for development, testing and reliability of the software.
Management of the common shared software deployment requires a plan for accommodating mission specific updates to certain component behaviors which may not be needed by all missions using the same common shared software deployment.
  For LF and NEA Scout, a copy of the common shared component was created for making mission specific updates which worked but was not ideal.
  Recommend use of child classes to manage mission specific updates to common components where possible
Common shared software deployment components and connections should be maintained in a separate subsystem topology that can be imported for mission specific add-ons.
  The LF deployment includes a copy of the common deployment as subsystem topologies were not used
  Any changes to the common deployment had to be duplicated in the LF deployment

## Slide 8: Lunar Flashlight Lessons Learned
Issues encountered during integration testing were reconstructed using component unit tests which allowed visibility and control on internal component state to assist with debug
  Do not underestimate the value of unit testing which is often overlooked in projects constrained due to budget and schedule especially when pressed to deliver hardware on an aggressive timeline.
Execute software on flight-like hardware in a flight-like manner as soon and as often as possible
  Maximize software test and debug time on hardware by streamlining testbed hardware access and test execution.
  Having an efficient and lean hardware test execution setup and process encourages software developers to test longer and more often on hardware leading to better tested software
  We discovered a hardware bug with EDAC once EDAC settings were enabled for the processor. The issue was discovered once I&T had already started, and testing with EDAC enabled early-on would have helped resolve the issue sooner.
  We often practiced ”test as you fly, fly as you test” approach in our development and testing of the FSW which immensely contributed to the success of FSW in operations.
When scoping out FSW development, it was critical to organize functionality by components grouped into releases
  Prioritizing development of common functionality and interfaces shared between LF and NEA Scout initially established a strong base for developing mission specific deployments
  Developing and testing uplink/downlink interfaces early-on was very valuable in defining how the rest of FSW receives and generates data for storage and downlink.

## Slide 9: Lunar Flashlight Lessons Learned
Having metrics for measuring component development progress was helpful for tracking rather than relying on a subjective measure of reporting progress
  25% – requirements and design completed
  50% – implementation completed
  75% – unit testing completed
  100% – close-out actions completed
Development progress reporting should not be influenced by optimism to simply mark tasks as completed or claim completion credit any more than what’s already known to be completed and functional.
Having a workable plan that can be used to make progress is far more valuable than having the “right” plan
  The development plan was updated quite frequently during development as it was impacted by scope changes and receivable needs not being met
Managing scope was necessary to adjust delivery schedule in a traceable manner
  Used “additional scope” tickets in our issue tracking system to capture new updates needed in FSW not part of the original development plan
Linking receivable needs for FSW to component development and test activities along with tracking receive dates was critical to schedule tracking and adjusting development plans.

## Slide 10: Conclusion
Reusability and modularity of F Prime enabled development of flight software for Lunar Flashlight leveraging a multi-mission common software deployment
No FSW bugs reported for LF since launch which underlines the quality and reliability of the software and development process used for managing delivery of the software.
Image captured from LF star tracker camera